## Sheet1
Expected Start Date | Expected End Date | Activity | Actual Start Date | Actual End Date | Status | Remark
22/9/2022 | 23/9/2022 | SRS | 2022-09-22 | 2022-09-23 | Done | Approved(Function part will be updated as we do coding)
26/9/2022 | 27/09/2022 | Design | 2022-09-26 | 2022-09-27 | Done | Approved
28/09/2022 | 30/09/2022 | Coding | 2022-09-28 | 2022-09-30 | Done | Approved
2022-03-10 | 2022-04-10 | UT | 2022-10-03 | 2022-10-04 | Done | Approved
2022-06-10 | 2022-07-10 | IT | 2022-10-06 | 2022-10-07 | Done | Approved
2022-10-10 | 2022-10-10 | Getting project ready | 2022-10-10 | 2022-10-10 | Done | Approved
Date | Day | Activity
22/9/2022 | Thur | SRS | 2022-09-22 | 2022-09-22 | Done | Approved(Function part will be updated as we do coding)
23/9/2022 | Fri | SRS, update 1st column (requirements) of RTM, start thinking design | 2022-09-23 | 2022-09-23 | Done | Approved(Function part will be updated as we do coding)
26/9/2022 | Mon | Design - HLD, LLD, update 2nd column (section numbers) of RTM | 2022-09-26 | 2022-09-26 | Done | modification in use-case and class diagram
27/09/2022 | Tue | Design - Seqence, class, use-case diagrams | 2022-09-27 | 2022-09-27 | Done | Approved
28/09/2022 | Wed | Coding | 2022-09-28 | 2022-09-28 | Done | Done
29/09/2022 | Thur | Coding, UT testcases development | 2022-09-29 | 2022-09-29 | Done | Done
30/09/2022 | Fri | Coding, IT testcases development | 2022-09-30 | 2022-09-30 | Done | Integration is remaining
2022-03-10 | Mon | Code review, UT_IT test plan, update 3rd column (function names) | 2022-10-03 | 2022-10-03 | Done | Approved
2022-04-10 | Tue | UT testing, first iteration of defect correction, update 4th column (UT testcases) | 2022-10-04 | 2022-10-04 | Done | Approved
2022-06-10 | Thur | Second iteration of testing and defect correction, update 5th column (IT testcases) | 2022-10-06 | 2022-10-06 | Done | Approved
2022-07-10 | Fri | IT testing and first iteration of defect correction | 2022-10-07 | 2022-10-07 | Done | Approved
2022-10-10 | Mon | Update all previously created documents, Github upload, presentation | 2022-10-10 | 2022-10-10 | Done | Approved
2022-11-10 | Tue | Final Evaluation (mock demo in case BU SME not coming this day) | NA | NA | NA | NA
2022-12-10 | Wed | Final evaluation